## TB3-EL-TC-30020
Consolidated Power Projects Project Details |  |  |  | Client Project Details
CPP Project Name: |  |  |  | Client Project Title:
CPP Job No: |  |  |  | Client Project Number
Bay / Cubicle / Panel Name: |  |  |  | Site Location:
Bay / Cubicle / Panel Number:
ITP Prepared by: |  |  |  | Client Checked by: | Name:
Position: |  |  |  |  | Position:
Date: |  |  |  |  | Signature:
Checked by: |  | Name: |  |  | Date:
Position:
Signature:
Date:
Tested by:
Test Commencement Date:
LINE No: | Test Category / Function |  | Acceptance Criteria |  |  | Result / Notes | Pass/Fail
1 | Control Cabinet
2 | External connections |  | Correct and green lined as per schematics
3 | AC supply |  | Free of short circuits
4 | DC supplies |  | Free of short circuits
5 | Supply polarity |  | Correct at all MCBs
6 | Space heater(s) |  | Thermostat correctly set
7 | Cabinet light |  | Door switch works correctly
8 | Visual inspection |  | No damage to insulators or control boxes
9 | Circuit Breaker
10 |  |  | Matches: -Purchase Order -Functional Design Specification
11
12
13
14
15
16
17 | SF6 pressure |  | As per manufacturer's recommendations
18 | Manual spring charging |  | Clockwise rotation charges spring. Charged / discharged indicator works
19 | Manual operation |  | Operation counter ticks over Open/close indicator displays correctly in both positions
20 | Electrical operation
21 | Local / remote switch |  | Switch works correctly
22 | SF6 blocking |  | Low gas pressure blocks operation
23 | Anti-pumping |  | Apply & maintain close coil voltage. Trip breaker and ensure reclose does not occur
24 | Trip circuit 1 opening time (5 Operations) |  | As per supplied manual and Manufacturers Test document
25 | Trip circuit 2 opening time (5 Operations)
26 | Trip circuit 1 close-open time (2 Operations)
27 | Trip circuit 2 close-open time (2 Operations)
28 | Closing time (5 Operations)
29 | Minimum operating voltage
30 | Contact Resistance
31 | Spring recharge time & motor current
32 | Additional Tests
33
34
35
36
37
38
39
40
NOTES, COMMENTS OR OTHER INFORMATION
ITP Completed (name): (CPP Project Commissioning Officer)
Signature:
Date: